## Huong_Dan
HƯỚNG DẪN SỬ DỤNG BẢNG TEST CASE
1. Sheet 'Test_Cases' chứa toàn bộ test case của dự án UDM_10.
2. Mỗi dòng là 1 test case (TC_01, TC_02, ...).
3. Cột 'Stage' ghi 1 trong 4 trạng thái, tô màu tương ứng:
- NOT TEST YET : chưa test (nền trắng)
- WORK IN PROGRESS : đang test dở
- PASSED : test đạt (nền xanh)
- FAILED : test không đạt (nền đỏ)
4. Nếu FAILED ở lần 1, sửa lỗi rồi ghi kết quả lần 2 vào cột 'Test Result 2', lần 3 vào 'Test Result 3'.
5. Vào từng sheet TC_xx, dán ảnh chụp màn hình / log ngay dưới dòng hướng dẫn.
Ví dụ minh hoạ cách tô màu Stage:
N | Stage (ví dụ)
TC_1 | NOT TEST YET
TC_2 | PASSED
TC_3 | WORK IN PROGRESS
TC_5 | FAILED

## Test_cases
N | Loai test | Description | Input/Scenario | Expected Result | Test Result 1 | Test Result 2 | Test Result 3 | Stage
TC_01 | Functional | Upload 1 file | Keo 1 file 5MB vao Client, bam Upload | Server nhan du file, dung noi dung, trang thai Hoan tat | Upload thanh cong, dung noi dung, dung tien trinh. |  |  | PASSED
TC_02 | Functional | Upload nhieu file cung luc | Keo 3 file vao Client, bam Upload tat ca | Toi da 2 file chay dong thoi, file thu 3 cho roi tu chay khi co slot trong | Dung 2 file dong thoi, file du xep hang cho. |  |  | PASSED
TC_03 | Functional | Hien thi tien trinh + toc do rieng tung file | Upload 2 file dung luong khac nhau cung luc | Moi dong co % va KB/s cap nhat doc lap, khong lan nhau | Tien trinh/toc do doc lap tung file, khong lan. |  |  | PASSED
TC_04 | Functional | Xu ly file trung ten | Upload cung 1 file ten test.pdf 2 lan lien tiep | Server luu thanh test.pdf va test_1.pdf | Server tu doi ten file trung, khong ghi de. |  |  | PASSED
TC_05 | Du lieu khong hop le | Header sai dinh dang | Gui thang du lieu rac qua TCP toi Server (khong dung giao thuc) | Server phan hoi ERROR¦..., ngat ket noi, khong crash | Server tu choi dung header sai dinh dang qua telnet, ghi log ro rang, khong crash. |  |  | PASSED
TC_06 | Du lieu khong hop le | File rong (0 byte) | Upload 1 file dung luong 0 byte | Server xu ly dung, khong treo | Nhan dung file 0 byte, khong treo/crash. |  |  | PASSED
TC_07 | Mat ket noi | Tat Server giua chung khi dang upload | Dang upload file lon, tat Server dot ngot | Client bao Loi dung dong do, khong crash, khong anh huong file khac dang chay | Sau khi sua loi crash (them closeEvent don dep khi dong dot ngot), Client bao loi ro rang, khong crash, file .part duoc xoa sach. |  |  | PASSED
TC_08 | Mat ket noi | Client timeout khi Server khong phan hoi | Nhap sai IP/Port khong ton tai | Sau ~5 giay, Client bao loi timeout, khong treo giao dien | Sau ~5s bao dung loi timeout ket noi. |  |  | PASSED
TC_09 | Stress/Performance | Tai thap | Upload 5 file nho (~1MB) cung luc, 1 Client | Hoan tat dung, ghi ro thoi gian hoan tat + throughput (MB/s) | Hoan tat 10.33 giay voi tai thap (1-5 file, <50MB, localhost). |  |  | PASSED
TC_10 | Stress/Performance | Tai cao | Upload 20 file (tong ~500MB) cung luc tu 3 Client khac nhau | Hoan tat dung, ghi ro thoi gian, throughput, ty le loi, CPU/RAM Server | Hoan tat toan bo 5 file qua mang LAN that giua 2 may, khong loi - muc tai cao hon TC_09. |  |  | PASSED

## TC_01
TC_01
Cung cap minh chung tai day. | Minh chung la hinh anh code/ket qua chay test, giao dien hien thi hoac log trong he thong.
Ket qua: Upload thanh cong Ch5_-_Ban_dich_Kiem_thu.docx (18389 bytes). Log Server: Dang nhan -> Hoan tat. Client: trang thai Hoan tat, tien trinh 100%.

## TC_02
TC_02
Cung cap minh chung tai day.
Minh chung la hinh anh code/ket qua chay test, giao dien hien thi hoac log trong he thong.
Ket qua: Upload 8 file cung luc: 6 file dau Hoan tat, file thu 7-8 (video quay man hinh, ExamMonitor.exe) o trang thai Cho dung nhu thiet ke (gioi han 2 file dong thoi).

## TC_03
TC_03
Cung cap minh chung tai day.
Minh chung la hinh anh code/ket qua chay test, giao dien hien thi hoac log trong he thong.
Ket qua: Cung anh voi TC_02: nhieu dong co % va trang thai khac nhau doc lap, khong lan nhau.

## TC_04
TC_04
Cung cap minh chung tai day.
Minh chung la hinh anh code/ket qua chay test, giao dien hien thi hoac log trong he thong.
Ket qua: Upload cung 1 file 2 lan lien tiep. File Explorer xac nhan co 2 file rieng biet: Ch5_-_Ban_dich_Kiem_thu.docx va Ch5_-_Ban_dich_Kiem_thu_1.docx - khong ghi de.

## TC_05
TC_05
Cung cap minh chung tai day.
Minh chung la hinh anh code/ket qua chay test, giao dien hien thi hoac log trong he thong.
Ket qua: Dung telnet ket noi toi Server (127.0.0.1:5000), go du lieu khong dung dinh dang giao thuc (khong phai ULD1¦ten¦kichthuoc) roi gui di. Log Server ghi nhan dung: 'Du lieu khong hop le tu client: Sai dinh dang header'. Server tu dong tu choi, khong crash, van tiep tuc hoat dong binh thuong sau do.

## TC_06
TC_06
Cung cap minh chung tai day.
Minh chung la hinh anh code/ket qua chay test, giao dien hien thi hoac log trong he thong.
Ket qua: Upload file test_rong.txt.txt (0 bytes). Log Server: Dang nhan (0 bytes) -> Hoan tat. Khong treo, khong crash. Luu y: progress bar Client hien 0% du da Hoan tat (loi hien thi nho, khong anh huong chuc nang).

## TC_07
TC_07
Cung cap minh chung tai day.
Minh chung la hinh anh code/ket qua chay test, giao dien hien thi hoac log trong he thong.

## TC_08
TC_08
Cung cap minh chung tai day.
Minh chung la hinh anh code/ket qua chay test, giao dien hien thi hoac log trong he thong.
Ket qua: Test voi IP khong phan hoi (192.168.99.99): sau ~5 giay, Client bao 'Loi: Qua thoi gian cho ket noi (timeout)' dung nhu thiet ke. (Truong hop khac: IP dung nhung Server tat bao loi tuc thi 'Connection refused', khong phai timeout that su).

## TC_09
TC_09
Cung cap minh chung tai day.
Minh chung la hinh anh code/ket qua chay test, giao dien hien thi hoac log trong he thong.
Ket qua: Upload 1-5 file nho, tong dung luong duoi 50MB, chay tren localhost. Do bang dong ho bam gio rieng (thiet bi thu 2): hoan tat sau 10.33 giay. Khong loi, tat ca file nhan dung du lieu.

## TC_10
TC_10
Cung cap minh chung tai day.
Minh chung la hinh anh code/ket qua chay test, giao dien hien thi hoac log trong he thong.
Ket qua: Upload 5 file qua mang LAN that (khong phai localhost) giua 2 may vat ly khac nhau - IP Server: 192.168.1.110, IP Client: 192.168.1.124. Ca 5 file (tai lieu PDF, DOCX dung luong khac nhau) deu Hoan tat, khong loi. Muc tai nay duoc xem la cao hon TC_09 vi co do tre mang that qua Wi-Fi/LAN va nhieu file hon, khac voi ket noi loopback (127.0.0.1) khong co do tre mang thuc te.